## Summary
CyberTrust KSA — Gap Analysis Summary
Coverage of SRS v1.0 requirements by the delivered Django implementation
Status | Functional (FR) | Non-Functional (NFR) | Total
Implemented | 0 | 3 | 3
Partial | 8 | 10 | 18
Broken | 2 | 2 | 4
Missing | 2 | 14 | 16
Deployment | 0 | 16 | 16
Process/QA | 0 | 3 | 3
TOTAL | 12 | 48 | 60
Legend
Implemented | Built and functional
Partial | Partly built / gaps remain
Broken | Code exists but fails or has a defect
Missing | Not implemented at all
Deployment | Ops/infra concern, not app code
Process/QA | Organizational process item

## Functional Requirements
Functional Requirements
CyberTrust KSA — Requirements Traceability Matrix (SRS v1.0 vs. Implementation)
Req ID | Requirement | Module | SRS Priority | Status | Evidence / Notes (in code)
FR-001 | Landing page (overview, 5-step, ROI, badges) | Core | High | Partial | core/views.landing_page + templates/core/landing.html exist. BUT FR-001.3 shows "334 controls" hardcoded while DB has 197. FR-001.8 AR/EN toggle non-functional (LocaleMiddleware missing).
FR-002 | Standalone company registration | Core | Critical | Partial | register_company works & creates Company+User. BUT bypasses CompanyRegistrationForm (no validation): FR-002.8 email verification = MISSING; FR-002.10 CR 10-digit validation = MISSING; FR-002.11 duplicate CR raises uncaught IntegrityError (HTTP 500).
FR-003 | AI-powered classification engine | AI Engine | Critical | Partial | classify_company() calls OpenAI & stores risk/summary. BUT FR-003.3/3.5 does NOT create the company control set/checklist; FR-003.7 admin manual override = MISSING; FR-003.9 re-classify on profile change = MISSING.
FR-004 | Compliance controls DB (334 controls) | Compliance | Critical | Partial | Models complete; cross-mapping (ControlMapping) present (20 rows). BUT only 197/334 seeded (NCA 65/114, Aramco 66/92, SABIC 66/94). FR-004.7 Excel import/export = MISSING; FR-004.8 versioning = MISSING.
FR-005 | Evidence upload & OCR processing | Compliance+AI | Critical | Broken | PDF & image OCR (Tesseract) work. BUT FR-005.1 DOCX/XLSX unsupported (binary read as utf-8 -> fails); FR-005.2 50MB conflicts w/ DATA_UPLOAD_MAX=10MB; FR-005.11 type/size validation = MISSING; FR-005.12 thumbnails = MISSING; FR-005.13 delete w/ audit = MISSING.
FR-006 | AI-powered evidence analysis | AI Engine | Critical | Partial | analyze_evidence() implemented & wired into upload. BUT runs synchronously (blocks request); FR-006.9 batch analysis = MISSING; FR-006.11 API rate limiting = MISSING; FR-006.10 retry logic minimal (single try/except).
FR-007 | Gap analysis & predictive risk | AI Engine | High | Broken | generate_gap_analysis() implemented. BUG: run_gap_analysis only saves a GapAnalysis row for NCA; Aramco & SABIC never saved. FR-007.12 PDF export = MISSING.
FR-008 | Role-specific dashboards (4 roles) | Dashboard | High | Partial | Executive/Compliance/IT/BU dashboards exist and query real data. Partial: heatmap/ROI/benchmarks largely template-level; data sources (monitoring) are empty (see FR-010).
FR-009 | Auditor portal | Auditor Portal | High | Partial | Dashboard, review, notes, document request, submit_report implemented. BUT FR-009.10 digital signature = MISSING; certificate issuance on pass (UC-004 step 11) = MISSING; FR-009.13 PDF export = MISSING.
FR-010 | Continuous compliance monitoring | Monitoring | High | Missing | Models exist (ComplianceScore/Alert/MonthlyReport/CertificateTracker) but NOTHING populates them: no Celery tasks, no scheduler. FR-010.1 daily recalc, .2 monthly reports, .3 renewal countdown, .4 alerts, .5 email = ALL MISSING. realtime view crashes (template realtime.html missing).
FR-011 | Reporting & export (PDF/Excel/board) | Dashboard | Medium | Missing | No PDF/Excel generation libs (no reportlab/weasyprint/openpyxl) and no export code anywhere. Entire FR-011 not implemented.
FR-012 | User & access management | Core | High | Partial | RBAC role choices exist; login/logout work. BUT FR-012.3 MFA = MISSING; FR-012.4 12-char password policy = NOT enforced; FR-012.6 account lockout = MISSING; FR-012.7 password reset = MISSING; FR-012.8 user activity audit log = MISSING; FR-012.9 invite users = MISSING.

## Non-Functional Requirements
Non-Functional Requirements
CyberTrust KSA — Requirements Traceability Matrix (SRS v1.0 vs. Implementation)
Req ID | Requirement | Category | Target | Status | Notes
NFR-001 | Page load time | Performance | < 3s | Deployment | Not benchmarked; depends on deploy.
NFR-002 | API response time | Performance | < 2s | Partial | No REST API exists; template views only.
NFR-003 | AI analysis response | Performance | < 30s/control | Partial | Runs synchronously in request (no async/Celery).
NFR-004 | OCR processing time | Performance | < 10s/page | Partial | Synchronous; 300 DPI full-page OCR may exceed.
NFR-005 | Concurrent users | Performance | 500+ | Deployment | SQLite dev DB; not tuned/tested.
NFR-006 | File upload size | Performance | up to 50MB | Broken | DATA_UPLOAD_MAX_MEMORY_SIZE=10MB blocks 50MB.
NFR-007 | Dashboard refresh | Performance | < 5s | Deployment | Not benchmarked.
NFR-008 | Report generation | Performance | < 60s | Missing | No report generation implemented.
NFR-009 | DB query time | Performance | < 500ms | Deployment | Not benchmarked.
NFR-010 | Search response | Performance | < 2s | Missing | No global search feature found.
NFR-011 | Encryption at rest | Security | AES-256 | Missing | SQLite plaintext; no field/disk encryption.
NFR-012 | Encryption in transit | Security | TLS 1.3 | Deployment | No SECURE_SSL_REDIRECT/HSTS; relies on proxy.
NFR-013 | Authentication (JWT) | Security | JWT | Broken | SRS says JWT; impl uses Django SessionAuthentication, no JWT.
NFR-014 | Authorization (RBAC, least priv) | Security | RBAC | Partial | Roles exist; per-view permission checks are minimal (login_required only).
NFR-015 | Input validation | Security | server-side | Partial | Forms exist but registration bypasses them (raw POST).
NFR-016 | SQL injection prevention | Security | ORM params | Implemented | Django ORM used throughout.
NFR-017 | XSS prevention (CSP) | Security | CSP + encoding | Partial | Django autoescape on; no Content-Security-Policy header.
NFR-018 | CSRF protection | Security | Django CSRF | Implemented | CsrfViewMiddleware enabled.
NFR-019 | File upload security | Security | type/AV/size | Missing | No type whitelist, no virus scan, no size guard.
NFR-020 | API rate limiting | Security | 100/min/user | Missing | No DRF throttling / no rate limiting.
NFR-021 | Audit logging | Security | all actions | Missing | Only AI logs; no general user-action audit trail.
NFR-022 | Data backup | Security | daily/30d | Deployment | Operational; not in app.
NFR-023 | Penetration testing | Security | annual | Process/QA | Process item.
NFR-024 | Vulnerability scanning | Security | monthly | Process/QA | Process item.
NFR-025 | System availability | Availability | 99.5% | Deployment | Operational.
NFR-026 | Maintenance window | Availability | <4h/mo | Deployment | Operational.
NFR-027 | RTO | Availability | <4h | Deployment | No DR runbook in repo.
NFR-028 | RPO | Availability | <1h | Deployment | No backup cadence configured.
NFR-029 | Failover | Availability | auto DB failover | Deployment | Single SQLite in dev.
NFR-030 | Graceful AI degradation | Availability | degrade | Partial | try/except returns pending verdict; no queue/retry.
NFR-031 | Horizontal scaling | Scalability | load balancer | Deployment | Gunicorn/Nginx noted in SRS only.
NFR-032 | DB read replicas | Scalability | replicas | Deployment | Not configured.
NFR-033 | Storage scaling | Scalability | cloud/S3 | Missing | Uses local FileField; no S3 backend.
NFR-034 | User scaling | Scalability | 10,000+ cos | Deployment | Not tested.
NFR-035 | Control scaling | Scalability | 1,000+/fw | Implemented | Schema supports it; data is the limit.
NFR-036 | Language support (AR/EN, RTL) | Usability | full | Partial | Bilingual fields present; LocaleMiddleware MISSING so no live toggle.
NFR-037 | Responsive design | Usability | mobile/desktop | Partial | Tailwind templates; not verified across breakpoints.
NFR-038 | Accessibility | Usability | WCAG 2.1 AA | Missing | No a11y work evident.
NFR-039 | Browser support | Usability | latest 2 | Deployment | N/A in code.
NFR-040 | Onboarding tour | Usability | guided | Missing | Not implemented.
NFR-041 | Help documentation | Usability | context help | Missing | Not implemented.
NFR-042 | Error messages (bilingual) | Usability | clear/AR-EN | Partial | Messages mostly English only.
NFR-043 | Data sovereignty (KSA) | Compliance | in-KSA | Deployment | Hosting decision.
NFR-044 | NCA self-compliance | Compliance | ECC | Process/QA | Process item.
NFR-045 | PDPL compliance | Compliance | consent/min | Missing | No consent/min/deletion features.
NFR-046 | Audit trail | Compliance | complete | Missing | See NFR-021.
NFR-047 | Data retention policies | Compliance | configurable | Missing | Not implemented.
NFR-048 | Right to deletion | Compliance | support | Missing | Not implemented.

## Prototype & Use Cases
Prototype & Use Cases
CyberTrust KSA — Requirements Traceability Matrix (SRS v1.0 vs. Implementation)
Ref | Item (Prototype v3.2 / Use Case) | Status | Notes
Phase 0 | Landing page | Partial | Implemented; hardcoded 334 controls.
Phase 1 | Smart classification | Partial | AI runs; does not build company control set or N/A auto-marking.
Phase 2 | Integrations Hub (200+ tools, OAuth) | Missing | No integrations app/models at all.
Phase 3 | Automated control testing (continuous) | Missing | No background testing engine; no scheduler.
Phase 4 | Vulnerability management (CVE scan/map) | Missing | No vuln models/CVE ingestion.
Phase 5 | Gap analysis & predictive risk | Broken | Works but only saves NCA result (bug).
Phase 6 | Role-specific dashboards | Partial | 4 dashboards exist; data sources empty.
Phase 7 | Pre-audit simulator & auditor portal | Partial | Auditor portal exists; virtual simulator MISSING.
Phase 8 | Results & ROI dashboard | Partial | ROI numbers are static in templates.
Phase 9 | Security & certifications page | Missing | No dedicated page/route found.
Phase 10A | Continuous compliance hub | Partial | Page renders; no data generation/scheduler.
Phase 10B | Real-time monitoring (WebSocket feed) | Broken | No Channels/WebSocket; realtime.html template MISSING -> crashes.
UC-001 | Registration & classification | Partial | Missing email verify + control checklist creation.
UC-002 | Evidence upload & AI analysis | Partial | Works for PDF/img; DOCX/XLSX broken; synchronous.
UC-003 | Gap analysis generation | Broken | Aramco/SABIC not persisted; no PDF.
UC-004 | Auditor review | Partial | Review works; no certificate issuance / signature.
UC-005 | Continuous monitoring alert | Missing | No automated check/alert/email pipeline.